## Master Tracker
ID | Category | Service Name | Phase | Priority | Lab Status | Lab Owner | Lab Start | Lab Complete | Obera Status | Obera Owner | Obera Start | Obera Complete | Customer Status | Customer Owner | Notes | Dependencies
IAM-001 | Identity & Access | Microsoft Entra ID | Phase 1 | Critical | In Progress | Maverick | 2025-11-28 |  | Not Started |  |  |  | Not Started |  | Foundation for all Azure services [2025-11-28 02:45] LAB: Starting foundation identity setup | None
IAM-002 | Identity & Access | Entra ID P1/P2 | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Conditional Access, Identity Protection | IAM-001
IAM-003 | Identity & Access | Entra Connect / Cloud Sync | Phase 1 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Hybrid identity sync | IAM-001
IAM-004 | Identity & Access | Privileged Identity Management | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Just-in-time privileged access | IAM-002
IAM-005 | Identity & Access | Entra Domain Services | Phase 2 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Managed AD DS in cloud | IAM-001
SEC-001 | Security | Defender for Endpoint | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | EDR/XDR, integrates with Intune | IAM-001, EPM-001
SEC-002 | Security | Defender for Office 365 | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Email security, anti-phishing | IAM-001
SEC-003 | Security | Defender for Identity | Phase 1 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Protects on-prem AD | IAM-003
SEC-004 | Security | Defender for Cloud | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | CSPM + workload protection | MON-001
SEC-005 | Security | Microsoft Sentinel | Phase 2 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | SIEM/SOAR - Major MSP opportunity | MON-002
SEC-006 | Security | Azure Key Vault | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Secrets, keys, certificates | IAM-001
SEC-007 | Security | Defender for Cloud Apps | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | CASB for SaaS security | IAM-002
SEC-008 | Security | Azure Firewall | Phase 2 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Cloud-native firewall | NET-001
EPM-001 | Endpoint Mgmt | Microsoft Intune | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | MDM/MAM for all devices | IAM-001
EPM-002 | Endpoint Mgmt | Windows Autopilot | Phase 1 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Zero-touch provisioning | EPM-001
EPM-003 | Endpoint Mgmt | Windows 365 Cloud PC | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Fixed-price cloud desktops | IAM-001, EPM-001
EPM-004 | Endpoint Mgmt | Intune Suite | Phase 2 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Advanced analytics, remote help | EPM-001
VDI-001 | Virtual Desktop | Azure Virtual Desktop | Phase 3 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Full VDI solution | NET-001, STR-001, IAM-001
VDI-002 | Virtual Desktop | FSLogix Profile Containers | Phase 3 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Profile management for AVD | VDI-001
VDI-003 | Virtual Desktop | Nerdio Manager for MSP | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Third-party AVD automation | EPM-003
NET-001 | Networking | Azure Virtual Network | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Foundation: subnets, NSGs | None
NET-002 | Networking | Azure VPN Gateway | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Site-to-site VPN | NET-001
NET-003 | Networking | Azure DNS | Phase 1 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | DNS hosting, private zones | NET-001
NET-004 | Networking | Azure Bastion | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Secure RDP/SSH without public IPs | NET-001
NET-005 | Networking | Azure Private Link | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Private access to PaaS services | NET-001
NET-006 | Networking | Azure Load Balancer | Phase 2 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Layer 4 load balancing | NET-001
NET-007 | Networking | Azure ExpressRoute | Phase 3 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Dedicated private connection | NET-001
CMP-001 | Compute | Azure Virtual Machines | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | IaaS VMs | NET-001, STR-003
CMP-002 | Compute | Reserved Instances | Phase 1 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | 1-3 year commitments, 30-72% savings | CMP-001
CMP-003 | Compute | Azure Functions | Phase 3 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Serverless compute | IAM-001
CMP-004 | Compute | Azure App Service | Phase 3 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | PaaS for web apps | NET-001
CMP-005 | Compute | Azure Kubernetes Service | Phase 4 | Low | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Managed Kubernetes | NET-001, IAM-001
STR-001 | Storage | Azure Blob Storage | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Object storage, tiering | IAM-001
STR-002 | Storage | Azure Files | Phase 1 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Managed SMB/NFS shares | IAM-001, NET-001
STR-003 | Storage | Azure Managed Disks | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Block storage for VMs | None
STR-004 | Storage | Azure File Sync | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Sync on-prem to Azure | STR-002
BDR-001 | Backup & DR | Azure Backup | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Native backup for VMs, SQL | BDR-002
BDR-002 | Backup & DR | Recovery Services Vault | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Central backup management | None
BDR-003 | Backup & DR | Azure Site Recovery | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | DR orchestration | BDR-002, NET-001
BDR-004 | Backup & DR | Azure Backup for M365 | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | M365 backup (preview) | IAM-001
DB-001 | Databases | SQL Server on Azure VMs | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Full SQL Server IaaS | CMP-001
DB-002 | Databases | Azure SQL Database | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Managed SQL Server PaaS | NET-001
DB-003 | Databases | Azure SQL Managed Instance | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Near 100% SQL compatibility | NET-001
DB-004 | Databases | Azure Database for MySQL | Phase 3 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Managed MySQL | NET-001
MON-001 | Monitoring | Azure Monitor | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Metrics, logs, alerts | None
MON-002 | Monitoring | Log Analytics Workspace | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Central log aggregation | MON-001
MON-003 | Monitoring | Azure Lighthouse | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Multi-tenant MSP management | IAM-001
MON-004 | Monitoring | Azure Cost Management | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Cost analysis and optimization | None
MON-005 | Monitoring | Azure Arc | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Manage on-prem from Azure | MON-001
MON-006 | Monitoring | Azure Automation | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Runbooks, update management | MON-001
MON-007 | Monitoring | Azure Policy | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Governance at scale | IAM-001
MIG-001 | Migration | Azure Migrate | Phase 1 | Critical | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Discovery, assessment, migration | None
MIG-002 | Migration | Database Migration Service | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | DB migrations | DB-002
M365-001 | M365 Integration | Teams Phone System | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Cloud PBX | IAM-001
M365-002 | M365 Integration | Microsoft Purview | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Data governance, DLP | IAM-001
M365-003 | M365 Integration | Power Automate | Phase 2 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Workflow automation | IAM-001
M365-004 | M365 Integration | Power BI | Phase 3 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Business intelligence | IAM-001
DEV-001 | DevOps | Azure Logic Apps | Phase 2 | High | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | Integration workflows | IAM-001
DEV-002 | DevOps | Azure DevOps | Phase 3 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | CI/CD pipelines | IAM-001
AI-001 | AI & ML | Azure OpenAI Service | Phase 4 | Medium | Not Started |  |  |  | Not Started |  |  |  | Not Started |  | GPT-4, DALL-E APIs | IAM-001

## Dashboard
OberaConnect Azure Services Pipeline Dashboard
Pipeline Summary
Metric | Lab | Obera | Customer | Total
Not Started
In Progress
Testing
Complete
Blocked
Total Services
Services by Phase
Phase | Count | Critical | High | Medium | Low
Phase 1
Phase 2
Phase 3
Phase 4
Services by Category
Category | Total | Lab Complete | Obera Complete | Customer Ready
Identity & Access
Security
Endpoint Mgmt
Virtual Desktop
Networking
Compute
Storage
Backup & DR
Databases
Monitoring
Migration
M365 Integration
DevOps
AI & ML

## Phase 1 Focus
Phase 1: Foundation Services (Months 1-3)
These services form the foundation for all Azure deployments and should be mastered first.
Service | Category | Priority | Lab Status | Owner | Target Date
Microsoft Entra ID | Identity & Access | Critical | Not Started
Entra ID P1/P2 | Identity & Access | Critical | Not Started
Entra Connect / Cloud Sync | Identity & Access | High | Not Started
Defender for Endpoint | Security | Critical | Not Started
Defender for Office 365 | Security | Critical | Not Started
Defender for Identity | Security | High | Not Started
Microsoft Intune | Endpoint Mgmt | Critical | Not Started
Windows Autopilot | Endpoint Mgmt | High | Not Started
Azure Virtual Network | Networking | Critical | Not Started
Azure VPN Gateway | Networking | Critical | Not Started
Azure DNS | Networking | High | Not Started
Azure Virtual Machines | Compute | Critical | Not Started
Reserved Instances | Compute | High | Not Started
Azure Blob Storage | Storage | Critical | Not Started
Azure Files | Storage | High | Not Started
Azure Managed Disks | Storage | Critical | Not Started
Azure Backup | Backup & DR | Critical | Not Started
Recovery Services Vault | Backup & DR | Critical | Not Started
Azure Monitor | Monitoring | Critical | Not Started
Log Analytics Workspace | Monitoring | Critical | Not Started
Azure Lighthouse | Monitoring | Critical | Not Started
Azure Cost Management | Monitoring | Critical | Not Started
Azure Migrate | Migration | Critical | Not Started

## Runbook Template
Service Runbook Template
Service Name:
Service ID:
Category:
Phase:
PREREQUISITES
Required Licenses:
Required Permissions:
Dependencies:
Estimated Setup Time:
LAB DEPLOYMENT
Step 1:
Step 2:
Step 3:
Step 4:
Step 5:
Verification Tests:
OBERA DEPLOYMENT
Configuration Differences:
Security Considerations:
Integration Points:
CUSTOMER DEPLOYMENT
Customer Prerequisites:
Pricing Model:
SLA Requirements:
Support Escalation:
DOCUMENTATION
Internal Wiki Link:
Customer-Facing Doc:
Training Materials:
SIGN-OFF
Lab Completed By:
Lab Completed Date:
Obera Approved By:
Obera Approved Date:
Customer-Ready By:
Customer-Ready Date: